## Gantt Chart Template
Gantt Chart
Task name | Stard date | End date | Assigned | Status | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-24 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25
Astro App Web Dev | 2024-08-12 | 2024-10-01 | Shikhar | Open
Eight Screen UI Design in flutter |  |  | Arun | Open
Business Logic for Login, Sign Up, Kundali Generation. |  |  | Arun | Open
Mongo DB Test Database shall be created | 2024-09-10 | 2024-09-12 | Alok | Open
Node JS server shall be created with CRUD operation | 2024-08-12 | 2024-09-02 | Alok | Done
Production server shall be deployed to the Amazon Web Service. |  |  | Alok | Open
Test server shall be deployed to the Vercel platform. | 2024-08-26 | 2024-08-26 | Alok | Done
JWT token implementation for secured login | 2024-09-07 | 2024-09-09 | Alok | Open
Deploy the AI Astro Server to local host | 2024-09-07 | 2024-09-07 | Alok | Open
UI Design of 9 screen shall be created | 2024-08-12 | 2024-08-20 | Shikhar | Done
Project Report Compilation | 2020-08-12 | 2024-10-01 | Shikhar | Open
Insert new rows ABOVE this one

## Assignees and Status
Assignees | Status
Arun | Open
Alok | In process
Shikhar | Closed
Done