## Modules
Approximate Time Sheet based on the Requirement Provided
Phase | Module | Tasks | Description | Time (Hrs) | Days (No.) | Remarks
1 | Multi property management | Single Dashboard | A simple toggle is all that’s required to move from one property to the next. Select one and use all the App features activated for that community.
|  | Tag Rented Properties | If resident rent out any of the properties, he will continue to receive Community updates. However, visitors, daily help and deliveries will only be visible to the tenant.
|  | User Management | Resident
Tenant
1 | Helpdesk/Complaints Management | Quick complaint assignment | Resident will assign tickets right on the app.
|  | SMS alert to technicians | With App, the technician will receive an SMS as soon as one is assigned, and both the committee and resident will informed.
|  | Escalation Matrix and information | For timely resolution in case of issues where the assigned technician is not able to resolve the complaints on time or clarification is sought.
|  | Real-time updates | The management committee and resident get real-time updates on the ticket by the facility manager, so everyone is in the know. This keeps everyone on the same page and reduces the number of escalations.
|  | Detailed complaint reports | App makes it easy to analyze the performance of support staff and facility manager by downloading periodic complaint reports to understand resolution times and how they can be improved.
1 | Visitor Management | Use pass code invites | Replace the intercom and register book for a technologically-forward pass code-based solution that makes it easy for residents to participate in the process of approving their visitors.
|  | Verify unexpected visitors | The process is also simplified for visitors that simply turn up at the gate. Residents receive a notification on their app, requesting them to approve their entry. One click and they’re in.
App should be able to capture the following:
a. Data(name/address/contact no/purpose of visit/vehicle no/type of vehicle/etc)
b. Photo(visitor/vehicle/etc)
c. Documents details & snap(ID cards)
d. Safety instructions/Assembly points/important information for the day.
|  | Resolve parking issues | A visitor’s car is in a resident's spot? Fix this with ease on app,simply enter the vehicle number and get the owner’s contact details. Resolve the issue quickly.
1 | Communication Management | Notice Boards/Announcements | Can see all announcements/Notice related to residents through the app.
1 | Report | Transactional Summary/Detailed Report.
1 | Community Financial Management | Accounts, Invoicing & Online payments | Raise invoices for various society charges.
1 | Notifications & Bulk upload | Alerts, Notifications and escalations through email, push and app notification
Breakdown Ticket SMS for Technicians
Location based asset mapping bulk upload.
Asset with serial no. bulk upload. Auto generate QR code
Schedule Bulk upload
Asset with Spare parts bulk upload
2 | Buy, Sell & Rent | App will have provision in which customer can Buy, Sell & Rent various properties with co-ordination with brokers/property dealers – tie ups.
Also application will have provision in which occupants can buy & sell their HH goods, second hand cars etc. to internal occupants as well as external(third party applications), through this app.
2 | Amenities booking | Book your slot
Restrict usage to residents
Access usage history
Rewards- Redemption
2 | Asset Management | App will maintain a track history of various assets.
Asset details should be easily accessible.
Downloading of summary reports.
App will easily maintain & update health report of every asset
Asset tagging details with location.
Bar coding
2 | Child Security Management | Get notified on checkout attempt
Allow future exit
Auto-approved entries
Leave at gate
Overstay alert
2 | Communication Management | Run polls/Discussions
Start a discussion
Notice Boards/Announcements
Documents
2 | Contract & Compliance Management | Through app all documents will be easily accessible & get reminders for their renewal such as Lift License, HSD certificate etc. AMCs.
Can track PPM activities need to be carried out on monthly or quarterly basis.
Keep track of third party vendor contract copies & receive reminder for their approvals.
Can track status of 52 week maintenance schedule.
Through app emergency evacuation plan is easily accessible that will guide residents for safe evacuations.
2 | Daily Staff Management (Residents hired staff) | Instant notifications
Attendance review
Community staff ratings
2 | Health, Safety & Trainings | All trainings details will be accessible through this app.
Fire safety refresher videos will be provided in the app to be updated in case of any fire emergency.
Floor warden/ERT contacts will be easily accessible.
Fire MOC drill & other training attendance sheet will be uploaded for easy accessibility.
Health status of Daily helpers & drivers.
Medical Emergency services(outsiders). (also to include the Doctors list living in society)
Through app emergency evacuation plan should be easily accessible that will guide residents for safe evacuations.
Medical services-tie ups
2 | In-house & third party application accessibility | App will tie up with various food brands & supermarkets such as Spencers, Big Bazar, Zomato, Swiggy, etc: from which residents can directly order through our app& get various offers.
Shopping of various products can be done through application & get cashback/offers.
Printing & stationary (Xerox, Binding etc.) services will be provided / tie-up, through app.
Azea Botanica Privilege cards and schemes being offered by vendors-integrated.
2 | Mobility | Create, Assign, Execute Work Orders
Photo/Audio/Video Capture
Q R Scanning
Geo-Location Tracking for Service Technicians
Asset History
E-Signature Capture
2 | Recruitments | Data bank
Referrals & uploading of details by residents/others
Find suitability & employment-soft & technical services.
2 | SLA, Reminders,Escalations | SLA, multiple reminders and multiple escalations management of work.
Orders Ticket SLA.
2 | Socializing | will have feature in which occupants can send socializing request/schedules (Kitty party, Yoga session, etc) through this app.
E-library-a repository of all books on line.
2 | Stand alone service provider | Deep cleaning, general cleaning, pest control, chauffer, plumbing, electrician, carpentry, repair & maintenance, etc.
2 | Stock & inventory management | Stock details can be viewed by team members through this app.
Able to raise tickets for material requirement.
2 | Suggestions & Feedback | Create a platform for recording suggestions & feedbacks.
2 | Work Order Management | Manage PPM with inspection checklist & auto assignation of PPM work order to Technicians
Items Breakdown Management.
Adhoc work order.
Multitask work either serial or parallel
Meter based schedule & Monitoring point
Spare replacement schedule
Calibration schedule
Complete work log for breakdown work orders
Work orders in Calendar view.
PPM mapped to a specific user group.
2 | e-commerce platform | Link between business & customers
2 | Report | Work Order report in PDF.
Asset monitoring report.
Configuration report.
Asset/Engineer Performance Rating Reports
Spare Usage report.
2 | Community Financial Management | Accounts, Invoicing& Online payments | Set rules based on size of flat or usage.
Invoicing for groups or individuals.
Option to configure any kind of penalty.
Bulk charge items for invoicing.
Ability to collect payment online
Ability to accept payment by EMI
Collect partial payments
Mobile dashboard for residents
View dues based on selected date
|  | Payment collection | Capture all payment collection modes.
Accept partial payment of charges.
Acknowledge payment via email/SMS/Whatsapp.
Bulk downloads of receipts.
Link/Configure bank account for selected bills.
|  | Reports and reconciliation | View date-wise dues for an account or bill.
View payment collection by account.
View collections based on payment mode.
Auto-reconciliation.
Download reports to your device.
2 | Private Business Promotions | Private businesses like-vocational trainings, Sports coaches, Yoga, etc.

## TaskList (hidden)
Module | Mode | Task Type | TaskDesciption | Complexity | Time (in HRS) | Total Days | Remarks
Project Tools / Environment Setup | WEB | WEB | Set up an react native | Moderate | 6
|  |  | Set up an DB and required master tables | High | 6
|  |  | Create an API to connect between application | High | 6
|  |  |  | Total | 18 | 3
| WEB | UI | Create a screen to capture all required resident details | Moderate | 8
ResidentRegistration | MOBILE | UI | Create a screen to capture all required resident details | Moderate | 8
|  | Backend | Create required database tables and procedures to handle resident details | Moderate | 8
| WEB | UI | Create dashboard/homescreen for residentdetails | Moderate | 8
| MOBILE | UI | Create dashboard/homescreen for residentdetails | Moderate | 8
|  | API | Open APIs for resident screen add/edit/delete and view | Moderate | 8
|  | Testing | Unit testing for the screen | High | 6
|  |  |  | Total | 46 | 6
User Login |  | API | Setting firebased authentication to create a login for user | High | 24
| WEB | UI | Login screen | High | 6
| MOBILE | UI | Login screen | High | 6
|  | API | Open API to authenticate user | High | 6
|  | Gateway | email/SMS gateway integration for user authentication | High | 6
|  | Testing | Unit testing for the screen | High | 6
|  |  |  | Total | 54 | 7
| WEB | UI | Create a screen to capture all required resident family details | Moderate | 6
| MOBILE | UI | Create a screen to capture all required resident family details | Moderate | 6
| WEB | UI | Create a screen to view resident family details | Moderate | 6
ResidentFamilyRegistration | MOBILE | UI | Create a screen to view all resident family details | Moderate | 6
|  | Backend | Create required database tables and procedures to handle residentFamily details | Moderate | 6
|  | API | Open APIs for resident familyscreen add/edit/delete and view | Moderate | 6
|  | Testing | Unit testing for the screen | High | 6
|  |  |  | Total | 42 | 7
| WEB | UI | serviceProviders screen | Moderate | 6
serviceProviders | MOBILE | UI | serviceProviders screen | Moderate | 6 |  | Optional requirement
|  | Backend | Preparing master data and related tables | Moderate | 6
|  | API | Open APIs for staff registration add/edit/delete and view | Moderate | 6
| WEB | UI | Dashboard for serviceProviders | Moderate | 6
| MOBILE | UI | Dashboard for serviceProviders | Moderate | 6
|  | Testing | Unit testing for the screen | High | 6
|  |  |  | Total | 42 | 6
| WEB | UI | Visitor management screen | Moderate | 6
Visitor Management | MOBILE | UI | Visitor management screen | Moderate | 6
|  | Backend | Preparing database to save visitor details | Moderate | 6
|  | Gateway | SMS gateway integration in case token based security is provided | High | 6
| WEB | UI | Image capturing | Moderate | 6
| WEB | UI | ID card scanning | Moderate | 6
| MOBILE | UI | Image capturing | Moderate | 6
| MOBILE | UI | ID card scanning | Moderate | 6
|  | API | To Add and view | Moderate | 6
|  | API | Notification for unexpected visitors from security check | Moderate | 6
| WEB/MOBILE | API | Allot parking slots for the visitor vehicles. | Moderate | 6
| WEB/MOBILE | UI | To view the parking slots availability for visitors | Moderate | 6
| WEB | UI | To view the parking slots availability for visitors | Moderate | 6
| MOBILE | Testing | Unit testing for the screen under Menu management | Moderate | 6
|  |  |  | Total | 84 | 11
Menu Management | WEB | UI | Screen for adding menu |  | 6
| WEB | Backend | Preparing database and related table functions | High | 6
| WEB | API | Open APIs for staff registration add/edit/delete and view | High | 6
| WEB | UI | Menu view screen | High | 6
| WEB | Testing | Unit testing for the screen under Menu management | High | 6
|  |  |  | Total | 30 | 4
User_Menu screen | WEB | UI | Screen for giving access to menu for users | High | 6
| WEB | Backend | Preparing databse and related table functions | High | 6
| WEB | API | Open APIs for staff registration add/edit/delete and view | High | 6
| WEB | UI | User Menu view screen | High | 6
| WEB | Testing | Unit testing for the screen under Menu management | High | 6
|  |  |  | Total | 30 | 4
Raise invoices for various society charges | WEB | UI | Screen for invoice generation admin view | High | 6
| WEB | Backend | Create rule for invoice generation based on the requirement | High | 8 |  | Further discussion required.
| WEB | Backend | Preparing database and related table functions | High | 6
| WEB | API | Open APIs for invoice generation add/edit/delete and view | High | 6
| WEB | UI | Various invoices view screen | High | 6
| WEB | Gateway | Paymentgateway implementation | High | 6
| WEB | UI | Screen for invoice Payment user view | High | 6
| WEB | Backend | Preparing database and related table functions | High | 6
| WEB | API | Open APIs for invoice payment add/edit/delete and view | High | 6
| WEB | UI | Report of invoice generated admin view | High | 16
| WEB | UI | Payment history of user view and admin view | High | 8
| WEB | API | API for report generation | High | 16
| WEB | Gateway | SMS/EMAIL gateway integration for payment receipt | High | 8
|  | API | Auto reconciliation | High | 24 |  | It's an automated accounting process need an R & D
|  | Testing | Testing invoice module | High | 8
|  |  |  | Total | 136 | 17
Report |  | UI | Detailed Report design | High | 16
|  | API | to generate and transfer required report data | High | 6
|  | API | Create an work order report data | High | 6
|  | API | Asset monitoring report | Moderate | 6
|  | API | Configuration report. | Moderate | 6
|  | API | Asset/Engineer Performance Rating Reports | High | 6
|  | API | Spare Usage report. | Moderate | 6
|  | Testing | unit testing the module | Moderate | 6
|  |  |  | Total | 58 | 8
Stock & inventory management |  | UI | Screen to capture the stock details | Moderate | 6
|  | Backend | to prepare the stock master data | Moderate | 6
|  | API | to view/add/edit/update/delete the required data | Moderate | 6
|  | UI | To request for supply and request the required items | Moderate | 6
|  | UI | To approve the stock requirement | Moderate | 6
|  | UI | Home page to view available stock for both user and admin | Moderate | 6
|  | UI | page to view stock movement for both user and admin | Moderate | 6
|  | Gateway | To acknowledge the raised ticket against the stock both sms and email | Moderate | 6
|  | Testing | unit testing the module | Moderate | 6
|  |  |  | Total | 54 | 7
Asset Management |  | UI | Screen to capture the stock details | Moderate | 6
|  | Backend | to prepare the asset master data | Moderate | 6
|  | API | to view/add/edit/update/delete the required data | Moderate | 6
|  | UI | To request for supply and request the required items | Moderate | 6
|  | Gateway | To acknowledge the raised ticket against the stock both sms and email | Moderate | 6
|  | Geotagging | To track the asset location | High | 8 |  | R & D needed
|  | Barcode | Need enable creation and reading of bacode | High | 16 |  | Need to integrate third party tool for bacode
|  | UI | Option to view/download/edit the asset health reports | High | 16
|  | Testing | unit testing the module | Moderate | 6
|  |  |  | Total | 76 | 10
Contract & compliance management |  | API | all documents will be easily accessible & get reminders for their renewal such as License, HSD certificate etc. AMCs | High | 16
|  | UI | to view and download various documents | High | 8
|  | UI | to raise any complaint against the contract | Moderate | 6
|  | Gateway | EMAIL/SMS to acknowledge and communicate with in house and third party | Moderate | 6
|  | Backend | Database to prepare the data | Moderate | 6
|  | Testing | unit testing the module | Moderate | 6
|  | UI | Keep track of third party vendor contract copies & receive reminder for their approvals | High | 6
|  | API | Keep track of third party vendor contract copies & receive reminder for their approvals | High | 8
|  | UI | emergency evacuation plan is easily accessible that will guide residents for safe evacuations. | High | 8 |  | Discussion needed to set the plan and other details
|  | API | emergency evacuation plan is easily accessible that will guide residents for safe evacuations. | High | 8
|  | Testing | unit testing the module | Moderate | 6
|  |  |  | Total | 84 | 11
Work Order Management |  | UI | Manage PPM with inspection checklist | Moderate | 6
|  | API | Manage PPM with inspection checklist | Moderate | 6
|  | API | auto assignation of PPM work order to Technicians | Moderate | 6
|  | Gateway | SMS/EMAIL to notify the work orders | Moderate | 6
|  | UI | Create work orders with break down option | Moderate | 6
|  | API | Create work orders with break down option | Moderate | 6
|  | UI | Spare replacement schedule | Moderate | 6
|  | UI | To view spare details | Moderate | 6
|  | API | to add/edit/view the spare details | Moderate | 6
|  | UI | To create a caliberation schedule | Moderate | 6
|  | API | To create a caliberation schedule | Moderate | 6
|  | Backend | To save the caliberation schedule | Moderate | 6
|  | Report/Log | Complete log for break down work orders | High | 6
|  | Calendar integration | Work order schedule | High | 8
|  | UI | Assign Created work orders to group | High | 6
|  | API | To assign,view and edit work order to group | High | 6
|  | Backend | to save assigned work orders | High | 6
|  | UI | to view work orders assigned and it's schedule | High | 8
|  | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 120 | 15
SLA, Reminders,Escalations |  | API | SLA check | High | 8
|  | API | Send reminders and notifications | High | 8
|  | API | Escalations if required | High | 8
|  | Backend | TO save the reminders and escalated tickets | High | 8
|  | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 40 | 5
Notifications & Bulk upload |  | API | Alerts, Notifications and escalations through email, push and app notification | Moderate | 6
| WEB/MOBILE | Gateway | SMS/EMAIL | Moderate | 6
| WEB/MOBILE | UI | Location based asset mapping bulk upload | Moderate | 8
| WEB | API | Asset with serial no. bulk upload. Auto generate QR code | Moderate | 16
| WEB/MOBILE | API | To save and schedule bulk upload | Moderate | 16
| WEB/MOBILE | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 60 | 8
Communication management |  | UI | Create a screen to add and run poll/Meeting/Discussions | High | 24
| WEB | UI | Create a screen to add and run poll/Meeting/Discussions | High | 24
| MOBILE | API | To create/edit/view the polls and discussions | High | 16
|  | Backend | Create database and tables to save and view the data | High | 16
|  | UI | For chatroom in group and inperson | High | 16
| WEB | UI | For chatroom in group and inperson | High | 16
| MOBILE | API | For chatroom in group and inperson | High | 16
| WEB/MOBILE | Testing | unit testing the module | High | 12
|  |  |  | Total | 140 | 17
staff registration |  | UI | Staff registration screen | Moderate | 6
|  | Backend | Preparing master data and related tables | Moderate | 6
|  | API | Open APIs for staff registration add/edit/delete and view | Moderate | 6
|  | UI | Dashboard for staffdetails | Moderate | 6
| WEB | UI | Dashboard for staffdetails | Moderate | 6
| MOBILE | UI | Staff attendance Management | Moderate | 6
| WEB | UI | Staff attendance Management | Moderate | 6
| MOBILE | API | API to save/View/notify staff attendance | Moderate | 6
|  | GateWay | To notify staff attendance to responsible person. | Moderate | 6
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 62 | 8
Child security management |  | UI | Kid registration | Moderate | 6
| WEB | UI | Kid registration | Moderate | 6
| MOBILE | API | To view/add/edit the kids registration | Moderate | 6
|  | UI | Kids view personalised and admin view | Moderate | 8
| MOBILE | UI | Kids view personalised and admin view | Moderate | 8
| MOBILE | Backend | To save the kids details | Moderate | 6
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 48 | 6
Amenities booking |  | UI | Amenities master data | Moderate | 6
| WEB | Backend | To save the amenities master | Moderate | 6
|  | API | To add/edit/view the amenities | Moderate | 8
|  | UI | To view the amenities availability | Moderate | 8
| WEB | UI | To view the amenities availability | Moderate | 8
| MOBILE | Report | Access usage history | Moderate | 8
| MOBILE | Report | Access usage history | Moderate | 8
| WEB | API | Rewards- Redemption | Moderate | 8 |  | Logic need to finalised
|  | API | Usage history | Moderate | 6
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 74 | 10
Helpdesk/Complaints Management |  | UI | Quick complaint assignment | Moderate | 8
| WEB | UI | Quick complaint assignment | Moderate | 8
| MOBILE | API | Quick complaint assignment | Moderate | 8
|  | Backend | Save the complaint details | Moderate | 8
|  | Gateway | To notify the assigned technicians through SMS/EMAIL/Push notifications | Moderate | 8
|  | API | Escalation Matrix and information if not resolved in TIME | Moderate | 8
|  | API | Real-time updates to notify resident/Manager/Techinicians | Moderate | 8
|  | Report | Detailed complaint reports | Moderate | 8
| MOBILE | Report | Detailed complaint reports | Moderate | 8
| WEB | API | Detailed complaint reports | Moderate | 8
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 88 | 11
Multi property management |  | UI | Single Dashboard to switch between community/ group/property | High | 16
| WEB | UI | Single Dashboard to switch between community/ group/property | High | 16
| MOBILE | API | Single Dashboard to switch between community/ group/property | High | 16
|  | API | Tag Rented Properties | High | 16
|  | API | Restrict APP usage per the tagged property | High | 16
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 88 | 11
In-house & third party application accessibility |  | UI | Screen to display thirdparty app links | High | 24
| WEB | UI | Screen to display thirdparty app links | High | 16
| MOBILE | API | To connect with third party links | High | 16
|  | Backend | To set the access/maste data/offers | High | 16
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 80 | 10
Health, Safety & Trainings |  | UI | Screen to display Health, Safety & Trainings | High | 24
| WEB | UI | Screen to display Health, Safety & Trainings | High | 16
| MOBILE | API | To manage the training details | High | 32
|  | Backend | To upload/download videos | High | 24
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 104 | 13
Mobility
|  | UI | To Create,Assign track work orders | High | 8 |  | Need a discussion on logic
| WEB | UI | Google map integration for geo tacking | High | 16
| WEB | UI | To Create,Assign track work orders | High | 16
| MOBILE | UI | Google map integration for geo tacking | High | 16
| MOBILE | UI | Photo/Audio/Video Capture | High | 16
| WEB | UI | Q R Scanning | High | 16
| WEB | UI | Asset History | High | 16
| WEB | UI | E-Signature Capture | High | 16
| WEB | UI | Photo/Audio/Video Capture | High | 16
| MOBILE | UI | Q R Scanning | High | 8
| MOBILE | UI | Asset History | High | 8
| MOBILE | UI | E-Signature Capture | High | 8
| MOBILE | API | To integrate the | High | 24
|  | Testing | unit testing the module | High | 8
|  |  |  | Total | 192 | 24
Buy, Sell & Rent
|  | UI | screen to buy/sell/rent | Moderate | 16
| WEB | UI | screen to buy/sell/rent | Moderate | 16
| MOBILE | API | To integrate the functionality | Moderate | 16
|  | UI | To integrate the third party app to sell the cars HH goods etc | Moderate | 16
| WEB | UI | To integrate the third party app to sell the cars HH goods etc | Moderate | 16
| MOBILE | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 88 | 11
Socializing |  | UI | For socializing | Moderate | 24 |  | Logic and functionality need to be fixed
| WEB | UI | For socializing | Moderate | 16
| MOBILE |  | for third party integration | Moderate | 16
| API | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 64 | 8
Recruitments |  | UI | screen for registration for candidates | Moderate | 8
| WEB | API | for registration | Moderate | 8
| WEB | Backend | to keep the data for recruitment | Moderate | 8
| WEB | UI | to view the registered candiadate details | Moderate | 8
| WEB | API | for display/update the details | Moderate | 8
| WEB |  | to keep the data for recruitment | Moderate | 8
|  | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 56 | 7
Suggestions & Feedback |  | UI | Screen for sending suggestions and feedback | Moderate | 8
| WEB | UI | Screen for sending suggestions and feedback | Moderate | 8
| MOBILE |  | To save,edit and update the suggestions and feedback | Moderate | 8
| API | UI | Admin view for sending reply to suggestions and feedback | Moderate | 8
| WEB | UI | Admin view for sending reply to suggestions and feedback | Moderate | 8
| MOBILE |  | To save the details | Moderate | 8
| Backend | Testing | unit testing the module | Moderate | 8
|  |  |  | Total | 56 | 7
Stand alone service provider |  | UI | Integrating third party for Deep cleaning, general cleaning, pest control, chauffer, plumbing, electrician, carpentry, repair & maintenance, | Moderate | 16
| WEB | UI | Integrating third party for Deep cleaning, general cleaning, pest control, chauffer, plumbing, electrician, carpentry, repair & maintenance, | Moderate | 16
| MOBILE | API |  | Total | 32 | 4

## Amenity Book Process (hidden)
STEP-1 | STEP-2 | STEP-3 | STEP-4 | STEP-5 | STEP-6 | STEP-7